## Schedule
Date	Day	City	Promoter	Guarantee	Notes	Status	Drive Time (Hours)	Locals
03/01/24	Fri	Pittsburgh PA
03/02/24	Sat	Youngston OH	Nathan OfferDahl (email)	100% door		booked
03/03/24	Sun	Mansfield OH	Mothership	$250.00	need to reach back out	in progress
03/04/24	Mon	Detroit MI	Smalls	$250.00	Waiting for contact	in progress
03/05/24	Tue	OFF DAY	--------	------	----------------------------------------------------	--------
03/06/24	Wed	OFF DAY	--------	------	---------------------------------------------------	---------
03/07/24	Thu	Sheboygan WI	Punky Drewster	$250.00
03/08/24	Fri	Stevens Point,WI	Hell’s Disco	100% door		booked
03/09/24	Sat	Minneapolis MN		$250.00
03/10/24	Sun	Sioux City IA	Lizzy Alexandria	$250.00		booked
03/11/24	Mon	Aberdeen SD	Red Rooster Coffee House	90% Door		booked
03/12/24	Tue	Rapid City SD	RCGS	$250.00		booked
03/13/24	Wed	Casper WY	Brandon Schulte	$250.00	Reach out in january	in progress
03/14/24	Thu	Pueblo CO	Ricardo Alvarado	$250.00		in progress
03/15/24	Fri	Denver CO	Adam Kitchen	$100.00		booked
03/16/24	Sat	Durango CO	Silas Armstrong	$250.00		in progress
03/17/24	Sun	Salt Lake City UT	BeanKat Aleman	$250.00	still waiting on venue confirmation	in progress
03/18/24	Mon	OFF DAY	-------------------------------------	------	-------------------------------------------------------	----------------
03/19/24	Tue	Wenatchee WA	wallys tavern	$250.00	called, they will email me	in progress
03/20/24	Wed	Chehalis WA	McFlier’s	$250.00	Waiting for contact
03/21/24	Thu	Portland OR	Evin Grando	$250.00	Messaged 11/21	in progress
03/22/24	Fri	Tacoma WA	plaid pig	$250.00	info coming back from wenatchee peeps	in progress
03/23/24	Sat	Eugene OR	C.A. Krieger	$150.00		booked
03/24/24	Sun	OFF DAY	-------------------------------------	------	----------------------------------------------	----------------
03/25/24	Mon	OFF DAY	---	------	------------------------------------------------	----------------
03/26/24	Tue	Dunsmuir CA	Bernie Bleak	$250.00	Messaged 11/21
03/27/24	Wed	Nevada City CA	Ribald Brewing	$250.00	Waiting for contact
03/28/24	Thu	Bay Area		$250.00	emailed gilman
03/29/24	Fri	Santa Cruz CA		$250.00	messaged catalyst club
03/30/24	Sat	Fresno CA	TBA	$250.00	Destructive Productions	In Progress
03/31/24	Sun	Orange County CA		$250.00	messaged a bunch of people
04/01/24	Mon	OFF DAY	---------------------------------------------	-----------------------	---------------------------------------------------------	-------------------------------
04/02/24	Tue	Los Angeles CA		$250.00	messaged a bunch of people
04/03/24	Wed	Menifee CA		$250.00	messaged a bunch of people
04/04/24	Thu	OFF DAY	---	--------------	-----------------------------------------------------------	--------------------------------
04/05/24	Fri	San Diego CA	che cafe	$250.00		in progress
04/06/24	Sat	Yuma AZ	jason garcia	$200.00	maverick inn	booked
04/07/24	Sun	Phoenix AZ	Jesse Yonkaz	$250.00		in progress
04/08/24	Mon	Cameron AZ	JanMichael Reed	$250.00		booked
04/09/24	Tue	Shiprock NM	Jordan Steele	$250.00		in progress
04/10/24	Wed	Albuquerque NM	Heru Black	$250.00	crashing with heru	booked
04/11/24	Thu	OFF DAY	---	----------	-----------------------------------------------------------	-------------------------------------
04/12/24	Fri	Denton TX	Rubber Gloves Rehearsal Studios	$250.00		in progress
04/13/24	Sat	Austin TX		$250.00	reached out to daniel mesich
04/14/24	Sun	Houston TX	Johnae Whitaker	$250.00	Pretty sure were booked	booked
04/15/24	Mon	OFF DAY	---	----------	----------------------------------------------------------	-----------------------------------------
04/16/24	Tue	Oklahoma City OK	Destiny Hunt	90% Door	100% door if under $100, crash with destiny	booked
04/17/24	Wed	Hays KS	KC Tomanek	$250.00	messenger, reach back out in december	in progress
04/18/24	Thu	St Joseph MO	Sk8Bar	$250.00	contact on messenger	booked
04/19/24	Fri	St Louis MO		$250.00
04/20/24	Sat	Indianapolis IN		$250.00